## Jan - June 2022
THE NELSON MANDELA AFRICAN INSTITUTION OF SCIENCE AND TECHNOLOGY (NM - AIST) CENTRE FOR RESEARCH ADVANCEMENT, TEACHING AND SUSTAINABILITY IN FOOD AND NUTRITION SECURITY (CREATES-FNS)
IMPLEMENTATION OF ANNUAL PROCUREMENT PLAN REPORT JAN-JUNE 2022 Annual Procurement Plan (APP) is a guiding tool in any Procuring Entity. It is a layout of what should be procured and the methods of procurement to be used. All items to be procured emanate from the approved budget of the Centre. All items/activities with procurement element are included in the plan by consolidating items of similar nature, assigning a common name and then determine the method of procurement focusing on the amount budgeted. Preparation and implementation of the Annual Procurement Plan is mandatory to all procuring entities according to Public Procurement Act No.7 of 2011 and Regulation No. 446 of 2013 In the Financial Year 2022 CREATES-FNS prepared its APP which comprises of four parts: -
[6 empty] | DESCRIPTION | AMOUNT IN TZS
[6 empty] | Procurement of Goods | 1792386978
[6 empty] | Procurement of Works | 0
[6 empty] | Procurement of Non-Consultancy | 394958500
[6 empty] | Procurement of Consultancy Services | 10825000
[6 empty] | Total | 2198170478
ANNUAL PROCUREMENT PLAN FOR INTERNAL USE
GOODS
S/N | TENDER NAME | TENDER NO. | LOT | PLAN VS ACTUAL | DESCRPTION | BASIC DATA |  |  | GENERAL PROCUREMENT NOTE ADVERT | PREQUALIFICATION | [5 empty] | TENDERING DOCUMENT |  | INVITATION FOR TENDER AND EVALUATION |  |  |  | CONTRACT FINALISATION | [6 empty] | GENERAL REMARK
[6 empty] | ESTIMATED AMOUNT(TZS) | PROCUREMENT METHOD | SELECTION METHOD |  | DOCUMENT |  | INVITATION |  | EVALUATION |  | PREPARATION AND SUBMISSION BY PMU | APPROVAL BY TB | INVITATION FOR TENDERING |  | TENDER EVALUATION AND APPROVAL AWARD |  | NOTICE OF INTENTION TO AWARD DATE | VETTING/RATIFICATION OF CONTRACT | LPO NO. | SUPPLIER/SERVICE PROVIDER/CPNTRACTOR | CONTRACT AMOUNT(TZS) | DATE CONTRACT /LPO SIGNATURE | STATUS
[10 empty] | PREPARATION BY PMU | APPROVAL BY TB | INVITATION DATE | CLOSING-OPENING | SUBMISSION OF EVALUATION REPORT | APPROVAL BY TB |  |  | TENDER INVITATION DATE | TENDER CLOSING-OPENING | SUBMISSION TENDER EVALUATION REPORT | APPROVAL BY TB
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | TENDER FOR SUPPLY OF OFFICE STATIONARIES AND CONSUMABLES | PA/112/2022/HQ/G/01 | 1 | PLAN |  | 23110000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 26/1/22 | 2022-02-02 | 2022-03-02 | 2022-07-02 | 14/2/22 | 15/2/22 |  |  |  | 2022-02-02
|  |  |  | ACTUAL | PROCUREMENT OF DIARIES AND CALENDARS |  | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 22/01/2022 | 26/01/2022 | 26/01/2022 | 6/2/2022 |  |  | 13425 | ROBITEK LIMITED | 1450000 | 14/02/2022 | GOODS DELIVRED | 1. No Dates for Pre - Qualification, Because it was conducted by the Government Procurement Services Agency (GPSA). 2. No dates for Preparation of Tendering Document, Because The Standard Mini Competition for Framework Tenders issued by GPSA is being used. 3. No LPO numbers to Procurement via MVP Since Imprests were used. 4. All Procurements carried via Single there was no invitation, Only LPO issued. 5. Tender For Supply of DDI Machines and Tools Show Partial Implementation on the status, Because it is in initial stages of request and invitation on taneps. 6. Selection Method Show Not Applicable for Goods and Non Consultancy except for Consulatancy. 7. Some Tenders shows Various Suppliers in Column of Supplier, Because Procurement was conducted through Imprest, different suppliers were involved and no LPO issued. 8. Some Tenders are not implemented on their status, because they will be implemented in the remaining months. 9. Framework agreements for Catering and Transport Services does not have proper dates records only LPOs were issued upon requirements.
|  |  |  | ACTUAL | PROCUREMENT OF MOTOR VEHICLE LOG BOOKS |  | MVP | Not Applicable | 2022-01-07 | [14 empty] | 13487 | GPSA | 73500 | 30/5/2022 | GOODS DELIVRED
|  |  |  | ACTUAL | PROCUREMENT OF BUHERI WA AFYA PACKAGES |  | MVP | Not Applicable | 2022-01-07 | [15 empty] | VARIOUS SUPPLIERS | 1500000 |  | GOODS DELIVRED
|  |  |  | ACTUAL | PROCUREMENT OF CERTIFICATES AND BUNNERS |  | MVP | Not Applicable | 2022-01-07 | [15 empty] | VARIOUS SUPPLIERS | 950000 |  | GOODS DELIVRED
|  |  |  | ACTUAL | PROCUREMENT OF VARIOUS OFFICE CONSUMABLES |  | MVP | Not Applicable | 2022-01-07 | [15 empty] | VARIOUS SUPPLIERS | 2324500 |  | GOODS DELIVRED
2 | TENDER FOR OFFICE EQUIPMENT AND ACCESSORIES | PA/112/2022/HQ/G/02 | 1 | PLAN |  | 57755000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 26/1/2022 | 2022-01-01 | 2022-01-01 | 2022-06-01 | [5 empty] | 2022-08-01
|  |  |  | ACTUAL | PROCUREMENT OF ZKTECO SUPPLY UNIT |  | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 2022-06-01 | 2022-11-01 | 2022-11-01 | 2022-03-02 |  |  | 13423 | MICA COMPUTERS SERVICES | 393220.34 | 2022-11-02 | GOODS DELIVRED
3 | TENDER FOR SUPPLY OF FUEL | PA/112/2022/HQ/G/03 | 1 | PLAN |  | 16177000 | SINGLE SOURCE | Not Applicable | 2022-01-07 | [17 empty] | 25/4/2022
|  |  |  | ACTUAL | PROCUREMENT OF DIESEL FOR DFPA 3953 TO SUPPORT CENTRES ACTIVITIES |  | SINGLE SOURCE | Not Applicable | 2022-01-07 | [14 empty] | 13485 | GPSA | 5000000 | 25/5/2022 | GOODS DELIVRED
4 | TENDER FOR SUPPLY OF VARIOUS SOFTWARES AND LICENCE RENEWAL | PA/112/2022/HQ/G/04 | 1 | PLAN |  | 57775000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 26/8/2022 | 2022-01-09 | 2022-01-09 | 2022-07-09 | [5 empty] | 14/9/2022
|  |  |  | ACTUAL | PROCUREMENT OF ANT VIRUS FOR CENTRE'S OFFICE COMPUTERS |  | MVP | Not Applicable | 2022-01-07 | [15 empty] | MICA COMPUTERS SERVICES | 150000 |  | GOODS DELIVRED
5 | TENDER FOR SUPPLY OF RESEARCH EQUIPMENTS | PA/112/2022/HQ/G/05 | 1 | PLAN |  | 92440000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 20/1/2022 | 25/1/2022 | 25/1/2022 | 2022-06-02 | [5 empty] | 15/2/2022
|  |  |  | ACTUAL |  |  |  | Not Applicable | 2022-01-07 | [18 empty] | NOT IMPLEMENTED
8 | TENDER FOR SUPPLY OF LAB EQUIPMENTS AND REAGENTS | PA/112/2022/HQ/G/08 | 1 | PLAN |  | 11555000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 2022-01-08 | 2022-06-08 | 2022-06-08 | 2022-11-08 | [5 empty] | 13/8/2022
|  |  |  | ACTUAL |  |  |  | Not Applicable | 2022-01-07 | [18 empty] | NOT IMPLEMENTED
9 | TENDER FOR PROCUREMENT OF MOTOR VEHICLES | PA/112/2022/HQ/G/09 | 1 | PLAN |  | 462200000 | SINGLE SOURCE | Not Applicable | 2022-01-07 | [11 empty] | 2022-03-04 | [5 empty] | 2022-08-04
|  |  |  | ACTUAL | PROCUREMENT OF MOTOR VEHICLE FOR VC'S OFFICE |  | SINGLE SOURCE | Not Applicable | 2022-01-07 | [11 empty] | 2022-02-05 |  |  |  | GPSA | 267659595 | 25/5/2022 | PAID NOT DELIVERED
10 | TENDER FOR SUPPLY OF ICT EQUIPMENTS | PA/112/2022/HQ/G/10 | 1 | PLAN |  | 115550000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 2022-02-03 | 2022-07-03 | 2022-07-03 | 14/3/2022 | [5 empty] | 18/3/2022
|  |  |  | ACTUAL |  |  |  | Not Applicable | 2022-01-07 | [18 empty] | NOT IMPLEMENTED
11 | TENDER FOR SUPPLY AND DELIVERY OF FARM SUPPLIES AND EQUIPMENTS | PA/112/2022/HQ/G/12 | 1 | PLAN |  | 127105000 | RNCT | Not Applicable | 2022-01-07 | 2022-01-01 | 2022-06-01 | 2022-07-01 | 14/1/2022 | 20/1/2022 | 17/1/2022 | 18/1/2022 | 22/1/2022 | 23/1/2022 | 31/1/2022 | 2022-01-02 | 2022-06-02 | 2022-12-02 | 14/2/2022 |  |  |  | 20/2/2022
|  |  |  | ACTUAL | PROCUREMENT OF REDOX ALLUMINIUM PAINTED TABLES FOR GREEN HOUSES |  | RNCT | Not Applicable | 2022-01-07 | 2022-01-02 | 2022-08-02 | 14/2/2022 | 21/2/2022 | 21/2/2022 | 2022-09-03 | 2022-05-03 | 2022-11-03 | 15/3/2022 | 20/3/2022 | 20/3/2022 | 22/3/2022 |  |  | 13538 | ENHAKORE VETC | 19890000 | 2022-11-05 | GOODS DELIVRED
|  |  |  | ACTUAL | PROCUREMENT OF PLUMBING MATERIALS AND HYDROPONIC & FERTIGATION SYSTEMS |  | RNCT | Not Applicable | 2022-01-07 | 2022-01-02 | 2022-08-02 | 14/2/2022 | 21/2/2022 | 21/2/2022 | 2022-09-03 | 2022-05-03 | 2022-11-03 | 15/3/2022 | 20/3/2022 | 20/3/2022 | 22/3/2022 |  |  | 13565 | BAREFOOT INTERNATIONAL | 35196000 | 30/5/2022 | DELIVERED AND INSTALLED
12 | TENDER FOR SUPPLY OF BUILDING MATERIALS | PA/112/2022/HQ/G/13 | 1 | PLAN |  | 115550000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 26/1/2022 | 31/1/2022 | 31/1/2022 | 2022-05-02 | [5 empty] | 2022-09-02
|  |  |  | ACTUAL | PROCUREMENT FOR BUILDING MATERIALS TO BE USED FOR DESIGNATED STORAGE ROOM |  | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 29/11/2022 | 2022-03-12 | 2022-03-12 | 23/2/2022 |  |  | 13449 | DENZEL INVESTMENT | 3932989.83 | 2022-02-03 | GOODS DELIVRED
|  |  |  | ACTUAL | PROCUREMENT OF BUILDING MATERIALS FOR OLD CAFERTERIAL OFFICE RENOVATION |  | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 24/1/2022 | 27/1/2022 | 27/1/2022 | 2022-11-02 |  |  | 134431 | Z.S TRADERS | 6056183.49 | 14/2/2022 | GOODS DELIVRED
|  |  |  | ACTUAL | PROCUREMENT OF ALUMINIUM OF OLD CAFETERIA |  | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 2022-04-02 | 2022-08-02 | 2022-08-02 | 26/2/2022 |  |  | 13504 | MARK DISTRIBUTORS AND SUPPLIES CO.LTD | 34681641.8 | 28/2/2022 | GOODS DELIVRED
13 | TENDER FOR CONSTRUCTIONS OF TRAINING AND BUSINESS CENTRE HUB | PA/112/2022/HQ/G/14 | 1 | PLAN |  | 180581540 | RNCT | Not Applicable | 2022-01-07 | [8 empty] | 26/3/2022 | 30/3/2022 | 30/3/2022 | 2022-05-04 | [5 empty] | 2022-10-04
|  |  |  | ACTUAL | PROCUREMENT OF VARIOUS MATERIALS FOR GREEN HOUSES |  | MVP | Not Applicable | 2022-01-07 | [15 empty] | VARIOUS SUPPLIERS | 4719000 | Not Applied | GOODS DELIVRED
14 | TENDER FOR DESIGNING OF LAND SCAPING, WATER DRAINAGE AND RESERVOR SYSTEM | PA/112/2022/HQ/G/15 | 1 | PLAN |  | 122071642 | RNCT | Not Applicable | 2022-01-07 | 2022-01-02 | 2022-06-02 | 2022-07-02 | 14/2/2022 | 20/2/2022 | 17/2/2022 | 18/2/2022 | 22/2/2022 | 23/2/2022 | 29/2/2022 | 2022-01-03 | 2022-06-03 | 2022-12-03 | 14/3/2022 |  |  |  | 20/3/2022
|  |  |  | ACTUAL |  |  |  | Not Applicable | 2022-01-07 | [18 empty] | NOT IMPLEMENTED
15 | TENDER FOR CONSTRUCTION OF MINI RESEARCH LAB AT KAGERA | PA/112/2022/HQ/G/15 | 1 | PLAN |  | 86976796 | NCT | Not Applicable | 2022-01-07 | 2022-01-06 | 2022-06-06 | 2022-07-06 | 14/6/2022 | 20/6/2022 | 17/6/2022 | 18/6/2022 | 22/6/2022 | 23/6/2022 | 29/6/2022 | 2022-01-07 | 2022-06-07 | 2022-12-07 | 14/7/2022 |  |  |  | 20/7/2022
|  |  |  | ACTUAL |  |  |  | Not Applicable | 2022-01-07 | [18 empty] | NOT IMPLEMENTED
16 | TENDER FOR SUPPLY, DELIVERY AND COMMISSIONING OF INDUSTRIAL EQUIPMENTS, ACESSORIES AND TOOLS FOR DATA DRIVEN INNOVATION AND INCUBATION CENTRE | PA/112/2022/HQ/G/15 | 1 | PLAN |  | 323540000 | ICT | Not Applicable | 2022-01-07 | 2022-01-02 | 2022-06-02 | 2022-07-02 | 14/2/2022 | 20/2/2022 | 17/2/2022 | 18/2/2022 | 22/2/2022 | 23/2/2022 | 29/2/2022 | 2022-01-03 | 2022-06-03 | 2022-12-03 | 14/3/2022 |  |  |  | 20/3/2022
|  |  |  | ACTUAL |  |  |  | Not Applicable | 2022-01-07 | [18 empty] | PARTIAL IMPLEMENTED
NON CONSULTANCY
1 | TENDER FOR PROVISION OF CATERING SERVICES | PA/112/2022/HQ/NC/01 | 1 | PLAN |  | 69330000 | FWA-GPSA | Not Applicable | 2022-01-07 | No records | No records | No records | No records | No records | No records | No records | No records | 2022-10-02 | 17/2/2022 | 17/2/2022 | 2022-06-05 | no records | No records | No records |  |  | 20/5/2022
|  |  |  | ACTUAL | PROVISION FOR CATERING SERVICES FOR VERIFICATION SURVEY EXERCISE |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13535 | H.H SALIM SNACKS | 694279.66 | 24/5/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR CATERING SERVICES FOR NEED ASSESSMET WORKSHOP FOR MSC. CMAE |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13549 | H.H SALIM SNACKS | 440000 | 25/5/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | CATERING SERVICES FOR INNOVATION AND ENTEPREURSHIP TRAINING |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13456 | H.H SALIM SNACKS | 5506355.93 | 16/3/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | CATERING SERVICES FOR RESEARCH AND INNOVATION ON FEASIBILITY TRAINING |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13436 | H.H SALIM SNACKS | 578576.27 | 16/3/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | CATERING SERVICES FOR THE PRESENTATION OF FISH CAGE PRESENTATION PROJECT |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13452 | H.H SALIM SNACKS | 603305.08 | 16/3/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | CATERING SERVICES OFFERED IN MUSE SHIFTING MEETING |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13428 | H.H SALIM SNACKS | 617669.49 | 17/2/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | CATERING SERVICES FOR REGISTRATION OF NEW STUDENTS |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13401 | H.H SALIM SNACKS | 2155266.78 | 27/1/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | CATERING SERVICES FOR ORIENTATION OF NEW STUDENTS |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13405 | H.H SALIM SNACKS | 136323.36 | 27/1/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | CATERING SERVICES FOR ACE II VIRTUAL MEETING WITH WORLD BANK |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13368 | H.H SALIM SNACKS | 292527.21 | 17/1/2022 | SERVICE DELIVERED
2 | TENDER FOR PROVISION OF PRINTING SERVICES FOR CENTRE VISIBILITY MATERIALS | PA/112/2022/HQ/NC/02 | 1 | PLAN |  | 63330000 | CQ | Not Applicable | 2022-01-07 | 2022-01-02 | 2022-06-02 | 2022-07-02 | 14/2/2022 | 20/2/2022 | 17/2/2022 | 18/2/2022 | 22/2/2022 | 23/2/2022 | 29/2/2022 | 2022-01-03 | 2022-06-03 | 2022-12-03 | 14/3/2022 |  |  |  | 20/3/2022
|  |  |  | ACTUAL |  |  |  | Not Applicable | 2022-01-07 | [18 empty] | NOT IMPLEMENTED
3 | TENDER FOR PROVISION OF AIR TRAVEL AND HOTEL RESERVATION SERVICES | PA/112/2022/HQ/NC/03 | 1 | PLAN |  | 69330000 | CQ | Not Applicable | 2022-01-07 | 2022-01-02 | 2022-06-02 | 2022-07-02 | 14/2/2022 | 20/2/2022 | 17/2/2022 | 18/2/2022 | 22/2/2022 | 23/2/2022 | 29/2/2022 | 2022-01-03 | 2022-06-03 | 2022-12-03 | 14/3/2022 |  |  |  | 20/3/2022
|  |  |  | ACTUAL | PROVISION FOR AIR TRAVEL TICKETS FOR PROF. GABRIEL SHIRIMA TRAVELLING FROM KIA-DAR-KIA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 23/3/2022 | 25/3/2022 |  |  |  |  | 13483 | World Air Travel and Tours Ltd | 535500 | 2022-01-06 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR AIR TRAVEL TICKETS FOR PROF. HULDA SWAI FROM KIA-DAR-KIA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 2022-10-05 | 2022-11-05 |  |  |  |  | 13548 | World Air Travel and Tours Ltd | 521500 | 24/5/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR AIR TRAVEL TICKETS FOR PROF. HULDA SWAI FROM KIA-DAR-KIA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 21/2/2022 | 25/32/2022 |  |  |  |  | 13453 | World Air Travel and Tours Ltd | 587500 | 23/3/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR AIR TRAVEL TICKET FOR PROF. AGABA MORIS FROM UGANDA-KIA-UGANDA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 2022-11-02 | 2022-12-02 |  |  |  |  | 13432 | World Air Travel and Tours Ltd | 1681820 | 17/2/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR AIR TRAVEL TICKET FOR PROF. HULDA SWAI FROM KIA-DAR-NAIROBI-DAR-ARUSHA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 15/12/2022 | 17/12/2022 |  |  |  |  | 13384 | World Air Travel and Tours Ltd | 1247.78 | 17/1/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR AIR TRAVEL TICKET FOR MR. EDGAR KIPOKI FROM NAIROBI TO DAR |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 17/12/2022 | 20/12/2022 |  |  |  |  | 13385 | Beyond Travels | 301.78 | 17/1/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR AIR TRAVEL TIKETS FOR PROF. HULDA SWAI FROM KIA-MWANZA-BUKOBA-MWANZA-DAR-KIA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 31/12/2022 | 2022-05-01 |  |  |  |  | 13403 | Beyond Travels | 560.37 | 17/1/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION OF AIR TICKET FOR ROSE MOSHA AND TAMILWAI KINGAZI FROM KIA-DAR-MALAWI -KIA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 22 /01/2022 | 26/01/2022 |  |  |  |  | 13417 | Beyond Travels | 3675032 | 29/4/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION OF AIR TICKET FOR PROF. LINUS AND ATHANASIA MATEMU KIA -DAR -KIA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 28/03/2022 | 30/03/2022 |  |  |  |  | 13484 | World Air Travel and Tours Ltd | 949500 | 27/04/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION OF AIR TICKET FOR PROF. HULDA SWAI FROM KIA -DAR -KIA |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 28/03/2022 | 30/03/2022 |  |  |  |  | 13495 | World Air Travel and Tours Ltd | 633500 | 29/04/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR AIR TRAVEL TICKETS FOR PROF. HULDA SWAI FROM KIA-DAR-KIA (Changes fee) |  | CQ | Not Applicable | 2022-01-07 | [8 empty] | 2022-09-11 | 2022-10-11 |  |  |  |  | 13345 | World Air Travel and Tours Ltd | 180000 | 31/12/2022 | SERVICE DELIVERED
4 | TENDER FOR PROVISION OF PROMOTION ADVERTISING AND PUBLICATIONS SERVICES | PA/112/2022/HQ/NC/04 | 1 | PLAN |  | 23110000 | CQ | Not Applicable | 2022-01-07 | 2022-01-11 | 2022-06-11 | 2022-07-11 | 14/11/2022 | 20/11/2022 | 17/11/2022 | 18/11/2022 | 22/11/2022 | 23/11/2022 | 29/11/2022 | 2022-01-12 | 2022-06-12 | 2022-12-12 | 14/12/2022 |  |  |  | 20/12/2022
|  |  |  | ACTUAL | PROCUREMENT OF CAPS AND T SHIRTS |  | MVP | Not Applicable | 2022-01-07 | [16 empty] | 1600000 |  | SERVICE DELIVERED
5 | TENDER FOR PROVISION OF COURIER, FREIGHT FOWARDING AND CLEARING SERVICES | PA/112/2022/HQ/NC/04 | 1 | PLAN |  | 92440000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 2022-05-05 | 2022-09-05 | 2022-09-05 | 17/5/2022 | [5 empty] | 20/5/2022
|  |  |  | ACTUAL |  |  |  | Not Applicable | 2022-01-07 | [18 empty] | NOT IMPLEMENTED
6 | TENDER FOR SERVICING AND MAINTANANCE OF MOTOR VEHICLES | PA/112/2022/HQ/NC/05 | 1 | PLAN |  | 21954500 | SINGLE SOURCE | Not Applicable | 2022-01-07 | [8 empty] | 26/4/2022 | 30/4/2022 | 30/4/2022 | 2022-05-05 | [5 empty] | 2022-06-05
|  |  |  | ACTUAL | PROVISION FOR NORMAL CAR SERVICES FOR DFPA 3953 |  | SINGLE SOURCE | Not Applicable | 2022-01-07 | [14 empty] | 13438 | TEMESA | 546351.66 | 22/2/2022 | SERVICE DELIVERED
|  |  |  | ACTUAL | PROVISION FOR NORMAL CAR SERVICES FOR DFPA 3953 |  | FWA-GPSA | Not Applicable | 2022-01-07 | [14 empty] | 13406 | TEMESA | 545963.05 | 18/1/2022 | SERVICE DELIVERED
7 | TENDER FOR PROVISION OF INSURANCE SERVICES | PA/112/2022/HQ/NC/07 | 1 | PLAN |  | 13866000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 26/10/2022 | 30/11/2022 | 30/11/2022 | 2022-08-12 | [5 empty] | 16/12/2022
|  |  |  | ACTUAL | PROVISION FOR MOTOR VEHICLE INSURANCE FOR DFPA 3953 |  | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 26/4/2022 | 2022-02-05 | 2022-02-05 | 2022-05-05 |  |  | 13532 | ZANZIBAR INSURANCE CORPORATION | 5902219 | 2022-10-05 | SERVICE DELIVERED
8 | TENDER FOR SERVICING AND MAINTANANCE OF OFFICE EQUIPMENT & ACCESSORIES | PA/112/2022/HQ/NC/08 | 1 | PLAN |  | 16177000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 26/8/2022 | 30/8/2022 | 30/8/2022 | 2022-07-09
|  |  |  | ACTUAL | PROVISION FOR SERVICES AND MAINTANANCE OF NM AIST PRINTERS |  |  | Not Applicable | 2022-01-07 | [8 empty] | 23/8/2022 | 28/8/2022 | 28/8/2022 | 29/9/2022 |  |  | 13302 | THE 2 POWER COMMUNICATION | 5747308.81 | 2022-10-08 | SERVICE DELIVERED
9 | TENDER FOR PROVISION OF TRANSPORT SERVICE | PA/112/2022/HQ/NC/09 | 1 | PLAN |  | 6933000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 20/9/2022 | 24/9/2022 | 24/9/2022 | 29/9/2022
|  |  |  | ACTUAL | PROVISION FOR TRANSPORT SERVICES TO SUPPORT INNOVATION AND ENTEPRENUERSHIP TRAINING |  |  | Not Applicable | 2022-01-07 | [14 empty] | 13465 | ANGONI CAR HIRE TOURS AND SHUTTLE SERVICES LTD | 313500 |  | SERVICE DELIVERED
10 | MAINTANANCE OF CENTRE INTERNET/NM-AIST WEBSITES | PA/112/2022/HQ/NC/09 | 1 | PLAN |  | 18488000 | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 22/12/2022 | 26/12/2022 | 26/12/2022 | 30/12/2022
|  |  |  | ACTUAL | PROVISION OF INTERNET SERVICES |  | FWA-GPSA | Not Applicable | 2022-01-07 | [8 empty] | 28/9/2022 | 2022-05-10 | 2022-05-10 | 27/10/2022 |  |  | 13367 | GADGETRONIX.NET | 7258318.41 | 26/11/2022 | SERVICE DELIVERED
CONSULTANCY
1 | TENDER FOR DEVELOPMENT OF MONITORING AND EVALUATION SYSTEM | PA/112/2022/HQ/C/01 |  | PLAN |  | 10825000 | IC | ICS | 2022-01-07 |  | 24/2/2022 | 28/2/2022 | 2022-04-03 | 2022-11-03 | 15/3/2022 | 20/3/2022 | 25/3/2022 | 30/3/2022 | 2022-01-04 | 21/4/2022 | 21/4/2022 | 15/4/2022 | 20/4/2022 |  |  |  |  | 25/4/2022
|  |  |  | ACTUAL | [23 empty] | NOT IMPLEMENTED
| WORD | ABBREVIATION
1 | INDIVIDUAL CONSULTANT | IC
2 | INDIVIDUAL CONSULTANT SELECTION | ICS
3 | FREMWORK AGREEMENT | FWA
4 | GOVERNMENT PROCUREMENT SERVICES AGENCY | GPSA
5 | MINOR VALUE PROCUREMENT | MVP
6 | NATIONAL COMPETITIVE TENDERING | NCT
7 | RESTRICTED NATIONAL COMPETITIVE TENDERING | RNCT
8 | CO MPETITIVE QUOTATION | CQ
9 | INTERNATIONAL COMPETITIVE TENDERING | ICT
Formulas:
GENERAL PROCUREMENT NOTE ADVERT = [GENERAL PROCUREMENT NOTE ADVERT, row above]
TENDER EVALUATION AND APPROVAL AWARD = [TENDER CLOSING-OPENING]